## Summary
D Sculpt Fitness — Production Test Run
Tester |  |  | How to use
Date started
Build / URL tested |  |  | 1. Work through the "Test Runs" tab top to bottom.
Finance All-Time revenue BEFORE testing |  |  | 2. Set Result to Pass / Fail / Blocked / Not tested (dropdown).
Finance All-Time revenue AFTER cleanup |  |  | 3. On a Fail, write the ACTUAL numbers you saw in "Actual / notes" —
Member count BEFORE / AFTER |  |  | not "wrong", but "Finance showed Rs 7,500, expected Rs 5,000".
4. Set Severity on every Fail.
Results |  |  | 5. Money wrong, two screens disagreeing, or a member seeing data
Total tests | 176 |  | that is not theirs = Major at minimum.
Pass | 0 |  | 6. Screenshot every failure, including the browser console (F12).
Fail | 0 |  | 7. Prefix all test data with ZZTEST- and delete it at the end (section 18).
Blocked | 0
Not tested | 0
Blockers | 0
Majors | 0
Minors | 0
By area — failures
Area | Fail | Blocker+Major
0 | 0 | 0
1 | 0 | 0
2 | 0 | 0
3 | 0 | 0
4 | 0 | 0
5 | 0 | 0
6 | 0 | 0
7 | 0 | 0
8 | 0 | 0
9 | 0 | 0
10 | 0 | 0
11 | 0 | 0
12 | 0 | 0
13 | 0 | 0
14 | 0 | 0
15 | 0 | 0
16 | 0 | 0
17 | 0 | 0
18 | 0 | 0

## Test Runs
ID | Area | What to do | What must happen | Why it matters | Result | Actual / notes | Severity | Tester | Date
0 · Before you start — environment sanity
0.1 | 0 | Open the production URL in a fresh incognito window | Landing page loads, no console errors, logo and photos render
0.2 | 0 | Hard-refresh the dashboard 3 times in a row | Never lands on the landing page or a blank screen. (A router race used to do exactly this)
0.3 | 0 | Open the app, then go offline (airplane mode), then click around | Clear "offline" messaging, not a white screen or a silent failure
0.4 | 0 | Check the browser console on every page you visit today | Zero red errors. Note any that appear
0.5 | 0 | Install as a PWA (Add to Home Screen) and open it | Opens standalone, icon correct, works
0.6 | 0 | Log in, log out, log in again | Second login works without clearing cache
1 · Member login (member portal)
1.1 | 1 | Add a brand-new member as owner. **Write down the application number shown.** | The application number is shown clearly after saving and is not blank/`—`/`null` | Members were being created with no application number at all, so they could never log in and nobody knew
1.2 | 1 | Log in to the member portal with that number + phone | Lands on the member portal
1.3 | 1 | Log in as a member who was created **weeks ago**, not today | Works too | Old members and new members go through different code paths
1.4 | 1 | Type the phone **with +91**, with spaces, with a leading 0 | All three work | People paste from Contacts
1.5 | 1 | Type the application number in lowercase | Works
1.6 | 1 | Wrong application number, correct phone | Generic error. Must **not** say which field was wrong | Saying "phone is wrong" tells an attacker the number is real
1.7 | 1 | Correct application number, wrong phone | **Exactly the same** error text as 1.6 | Any difference is a security hole
1.8 | 1 | Fail login 6 times in a row | Locks out with a "too many attempts" message
1.9 | 1 | After lockout, wait it out and log in correctly | Works again — you are not locked out permanently
1.10 | 1 | **Edit that member** (change anything — name, notes, photo) and save. Then log in as them again | Login still works | Editing a member has previously overwritten the application number with blank and silently locked them out. This is the single highest-value test on this page
1.11 | 1 | Regenerate a member's application number, then try the **old** number | Old number rejected, new number works
1.12 | 1 | Log in as member A, then log out and log in as member B on the same device | B sees only B's data. No trace of A's name, plan, receipts or visits anywhere
1.13 | 1 | While logged in as a member, look for anything owner-only: the Add Member button, sidebar, finance figures | Nothing owner-only visible. The floating "+" button in particular has leaked into the member portal before
1.14 | 1 | Member portal → all four tabs (Check In, My Plan, Receipts, Visits) | All render, nothing blank, no console errors
1.15 | 1 | Log in as a member whose membership is **expired** | Shows "expired X days ago" — never a negative number like "-5 days remaining" | Fixed once; check both the My Plan tab and the Check In tab, they were separate bugs
2 · Add member → the money must appear everywhere
2.1 | 2 | Add `ZZTEST-A` on a ₹2,500 plan, fully paid, Cash | Saves, success message, application number shown
2.2 | 2 | Members list | Appears, correct plan, correct status, correct expiry
2.3 | 2 | Finance → This Month | Revenue went up by **exactly ₹2,500**. Cash total went up by ₹2,500. Card and Online unchanged
2.4 | 2 | Overview | Revenue figure matches Finance. Member count went up by 1
2.5 | 2 | Open the member → payment history | One payment, ₹2,500, Cash, today's date
2.6 | 2 | Generate the invoice | Amount ₹2,500, correct name, correct gym details, correct GST treatment
2.7 | 2 | Hard-refresh, re-check Finance and Overview | Same numbers. Nothing drifted
2.8 | 2 | Plan **+ an add-on** (e.g. ₹2,500 plan + ₹300 cardio) | Member detail modal must show ₹2,500 plan / ₹300 add-on / **₹2,800 total** — not ₹2,800 plan and ₹3,100 total. Add-ons were being counted twice in the modal while the invoice and DB were correct
2.9 | 2 | **Partial payment** — ₹2,500 plan, ₹1,000 paid now | Finance revenue +₹1,000 (not ₹2,500). Pending Dues +₹1,500. Member status "Partial". Alerts → Due shows them
2.10 | 2 | **Zero paid / full due** | Revenue unchanged. Dues +₹2,500
2.11 | 2 | **With a discount** | Invoice, member modal and Finance all agree on the discounted figure
2.12 | 2 | **Trial member** | Expiry is the trial date you set, not a plan-derived date. Doesn't pollute revenue if unpaid
2.13 | 2 | Card payment, then Online payment | Finance's Cash/Card/Online split matches exactly. These three must sum to total revenue
2.14 | 2 | Add a member **with no phone number** | Either blocked with a clear message, or saved — but then the portal-login prompt must say they can't be sent login details
2.15 | 2 | Add two members with the **same phone number** | Blocked with a readable message, not a raw database error
2.16 | 2 | Add a member with a **future join date**, and one with a **past join date** | Expiry calculated from the join date, not today. Shows in the right month in Finance
2.17 | 2 | Double-click **Save** rapidly | Exactly one member, one payment. Not two
2.18 | 2 | Turn off wifi mid-save, turn it back on | Either it saved once, or it didn't save at all. Never a member with no payment recorded, never two members
2.19 | 2 | Name with an apostrophe (`ZZTEST-O'Brien`) and one with `<b>bold</b>` in it | Displays literally. No broken layout, no bold text rendering, no crash. Check the list, the modal, the invoice and the CSV export
3 · Delete / remove a member
3.1 | 3 | Add `ZZTEST-B` with a ₹2,000 payment. Note Finance revenue
3.2 | 3 | **Remove** the member (the normal soft delete) | Gone from Members list, gone from Alerts, gone from member count
3.3 | 3 | Check Finance immediately, then after a hard refresh | Revenue **still includes** the ₹2,000 — this is correct and deliberate. The screen must *say so* somewhere, so the owner isn't left thinking it's a bug
3.4 | 3 | Use **Delete permanently** on another test member with a payment | Revenue drops by exactly that member's payments. Member, payments, invoices and check-ins all gone
3.5 | 3 | Try Delete permanently as **staff** 🔒 | Not available / refused
3.6 | 3 | Delete permanently, then hard refresh, then check Finance, Overview, Analytics, and the Payments CSV export | All five agree that the money is gone. Not "gone in Finance, still in Analytics"
3.7 | 3 | Remove a member, then check the Payments/Members CSV export and the Full Backup | The removed member is handled consistently — either present-and-marked or absent, in *every* export, not different per file
3.8 | 3 | Remove a member who has an **outstanding balance** | Pending Dues drops by their balance. Alerts count drops
3.9 | 3 | Cancel a membership (not delete) | Different from remove: check what Finance, Alerts and the member's own portal each show
3.10 | 3 | Remove the **last remaining** member | Finance/Overview show ₹0 or empty states cleanly, not "NaN", "undefined" or a broken chart
4 · Renewals
4.1 | 4 | Renew a member **before** their expiry, same plan, same price | Succeeds. New expiry = old expiry + plan duration (**not** today + duration — they must not lose the days they'd already paid for)
4.2 | 4 | **Renew the same member again** on the same plan and price a minute later | Must succeed. This exact case was permanently blocked as a "duplicate" — the single most common real-world pattern
4.3 | 4 | Renew a member **after** expiry | New expiry counts from today, not from the old expired date
4.4 | 4 | Double-click the Renew confirm button | Exactly one renewal, one payment
4.5 | 4 | After each renewal: Finance, Overview, payment history, invoice, member's own portal | All show the new payment and the new expiry. All agree
4.6 | 4 | Renew onto a **different, more expensive** plan | Amount, expiry and plan name all update everywhere
4.7 | 4 | Renew with a partial payment | Balance due created correctly, appears in Alerts and Finance Pending Dues
4.8 | 4 | Renew a **cancelled** member | Either sensibly reactivates them or is blocked with a clear message — not a silent failure
5 · Collecting a pending balance
5.1 | 5 | Member with ₹1,500 due — collect ₹500 | Balance now ₹1,000. Status stays Partial. Finance revenue +₹500. Dues −₹500
5.2 | 5 | Collect the remaining ₹1,000 | Balance ₹0, status Paid, member leaves the Alerts→Due list
5.3 | 5 | Try to collect **more** than the balance | Blocked or handled sensibly — never a negative balance
5.4 | 5 | Try to collect ₹0 or a negative amount | Blocked
5.5 | 5 | Open the same member on two devices/tabs and collect at the same time | Money counted once, not twice
5.6 | 5 | After collecting, check the invoice and payment history | Both show the new payment separately from the original
5.7 | 5 | As staff 🔒 collect a balance | Allowed (staff can collect) — but the Finance page must still be blocked for them
6 · Finance page
6.1 | 6 | Click through every period: Today / This Week / This Month / Last Month / Calendar Year / All Time | Each loads, no console errors, figures change sensibly
6.2 | 6 | Add up: does Cash + Card + Online = total Revenue? | Yes, in every period
6.3 | 6 | Net Profit = Revenue − Expenses? | Check by hand for one period
6.4 | 6 | "All Time" revenue vs the sum of every month | Must reconcile
6.5 | 6 | Custom range: pick a range that contains a known payment | That payment is included. Check both boundary days — the first and last day of the range must be inclusive. Off-by-one on the end date has broken this before
6.6 | 6 | Custom range with **end date before start date** | Blocked or handled, not a crash or a nonsense number
6.7 | 6 | Add an expense dated **today**, check This Month; then change it to last month | Moves between periods correctly
6.8 | 6 | Pending Dues card | It is **all-time**, not period-scoped. Confirm the label says so and the number matches the sum of every member's balance
6.9 | 6 | Click each stat card to expand the detail | Rows shown match the total above them
6.10 | 6 | Export CSV | Opens in Excel. Rows match what's on screen. Member names with commas/apostrophes don't break the columns. Filename sensible
6.11 | 6 | The 6-month Revenue vs Expenses chart | Doesn't change when you change the period buttons (it's a fixed 6-month trend) — and the label must say so
6.12 | 6 | As staff 🔒 try to reach Finance (sidebar and by typing the URL `/dashboard/finance`) | Blocked both ways
7 · Expenses
7.1 | 7 | Add an expense, check Finance | Expenses total and Net Profit both move
7.2 | 7 | Edit its amount | Finance updates
7.3 | 7 | Delete it | Finance returns to the previous figure exactly
7.4 | 7 | Expense on the **1st** and on the **last day** of a month | Both land in the right month. Month-boundary handling has broken here before
7.5 | 7 | Category name with `<script>` or `&` in it | Displays literally, does not break the page (this exact spot had an XSS bug)
7.6 | 7 | Very large amount, and a decimal amount (₹99.50) | Stored and displayed correctly, rounding consistent everywhere
7.7 | 7 | As staff 🔒 | Can add, **cannot** edit or delete
8 · Check-in (desk display + scanner)
8.1 | 8 | Open the desk display | QR appears, refreshes on its own (watch for ~1 min), screen doesn't sleep
8.2 | 8 | Press the **Back** button on the desk display | Returns to the dashboard **on the first press**. This is the button that failed at the client site
8.3 | 8 | Go to another section and come back to the desk display, then press Back again | Still works. The earlier failure only appeared after navigating around first
8.4 | 8 | Scan the QR from the member portal as an **active** member | Check-in succeeds, confirmation shown
8.5 | 8 | Scan again immediately | Handled — either a friendly "already checked in" or counted once. Never two visits for one entry
8.6 | 8 | Scan as an **expired** member | Rejected with a clear reason
8.7 | 8 | Scan a QR screenshot taken **2+ minutes ago** | Rejected (codes expire)
8.8 | 8 | Check in early morning (before 6am if you can) or change device time | The visit lands on today's date in India time, not yesterday. UTC/IST slippage has broken this class of thing before
8.9 | 8 | Staff manual check-in | Works, appears in Check-ins list
8.10 | 8 | After check-ins: Check-ins page, the member's Visits tab, and the attendance report | All show the same visits, same count, same dates
8.11 | 8 | Leave the desk display open for 10 minutes | Still refreshing, no memory bloat, no console errors piling up
8.12 | 8 | Desk display with wifi off | Shows the offline warning, doesn't show a stale QR as if it were valid
9 · Staff accounts and permissions 🔒
9.1 | 9 | Create a staff login, log in as them | Works
9.2 | 9 | As staff, check the sidebar | No Finance, Staff, Settings, Backup, Analytics
9.3 | 9 | As staff, **type the URLs directly**: `/dashboard/finance`, `/dashboard/staff`, `/dashboard/gymconfig`, `/dashboard/backup`, `/dashboard/analytics` | All blocked. Hiding the menu item is not enough
9.4 | 9 | As staff, look at Overview | No revenue figures anywhere
9.5 | 9 | As staff, open a member | Can edit, can renew, can collect — **cannot** delete or cancel
9.6 | 9 | Reset a staff password as owner, then log in as staff with the new password | Works; old password rejected
9.7 | 9 | Revoke/disable a staff login, then try to log in as them | Blocked. And if they were already logged in in another tab, they lose access on next action
9.8 | 9 | Delete a staff member who has added members | Their added members survive; "added by" doesn't crash the UI
9.9 | 9 | Log in as owner and staff in two browsers at once | Neither one's session breaks the other
10 · Plans
10.1 | 10 | Create a plan, add a member on it | Price and duration flow through to expiry, invoice and Finance
10.2 | 10 | **Change the plan's price**, then look at the existing member | Their historical payment must NOT change. Their invoice must still show what they actually paid
10.3 | 10 | **Delete a plan** that members are on | Those members still display correctly. Their detail modal and invoice don't break or show wrong totals — the fallback path for a deleted plan has had its own arithmetic bug
10.4 | 10 | Duplicate a plan, edit the copy | Original untouched
10.5 | 10 | Plan with 0 or negative price/duration | Blocked
10.6 | 10 | Plans Showcase page vs Plan Settings | Same plans, same prices
10.7 | 10 | As staff 🔒 | View only, no editing
11 · Enquiries
11.1 | 11 | Add an enquiry, move it New → Contacted → Converted | Counts on the four cards update every time
11.2 | 11 | Convert an enquiry into a member | Member created with the enquiry's details prefilled; enquiry marked converted; **not** duplicated as a fresh enquiry
11.3 | 11 | Filter by each status | Counts match the rows shown
11.4 | 11 | Delete an enquiry | Counts drop; nothing else affected
11.5 | 11 | Enquiry with a phone that's already a member | Handled sensibly, message is readable
12 · Alerts
12.1 | 12 | Compare the "Payment Due" count and total against Finance → Pending Dues | Identical. These two disagreeing is a classic
12.2 | 12 | Collect a member's balance | They disappear from the Due list immediately and after refresh
12.3 | 12 | Renew an expiring member | They leave the Expiring list
12.4 | 12 | Each filter pill (All / Expired / Expiring / Due) | Count on the pill = rows shown
12.5 | 12 | A member expiring **today** | Appears in exactly one bucket, not both Expired and Expiring
12.6 | 12 | Members with no phone number | "callable" count is accurate; call button doesn't appear or is disabled
12.7 | 12 | Click a member from Alerts | Opens the right member
13 · Invoices & WhatsApp
13.1 | 13 | Generate an invoice for a paid member | Gym name, address, GSTIN, logo, member details, amount, date all correct
13.2 | 13 | Check the address on the invoice | It must be an **address**, not an email. (Settings currently has an email in the address field — confirm whether it's been fixed)
13.3 | 13 | Invoice for a partially paid member | Shows paid vs balance correctly
13.4 | 13 | Invoice for a member with add-ons | Line items add up to the total actually charged. Cross-check against payment history
13.5 | 13 | Invoice with a discount applied | Discount shown, maths correct
13.6 | 13 | GST on / GST off in Settings | Invoice changes accordingly; totals still correct
13.7 | 13 | Print / save the invoice as PDF | Fits the page, nothing cut off, no dark-mode-only colours making it unreadable on paper
13.8 | 13 | Send login details / invoice via WhatsApp | Opens WhatsApp with the right number and a readable message; the application number and link in the message are correct
13.9 | 13 | Send WhatsApp to a member with no phone | Blocked with a clear message, not a broken link
13.10 | 13 | Invoice for a member whose plan was later deleted | Still correct (see 10.3)
14 · Settings
14.1 | 14 | Change gym name / address / phone, save, hard refresh | Persisted. Then check it flowed into: invoices, the landing page, the desk display, the audit report
14.2 | 14 | Upload a logo | Appears on dashboard, invoice, desk display, login screens. Try a large file and a non-image file — both handled
14.3 | 14 | Change GST settings | Invoice and the audit report both follow
14.4 | 14 | Fill in Legal Name / PAN / Registered Address | Audit report picks them up instead of "Not supplied"
14.5 | 14 | Edit the WhatsApp template, use every placeholder (`{name}`, `{appnum}`, etc.) | All substitute correctly with real values — no literal `{appnum}` left in the sent message
14.6 | 14 | Change reminder days | Alerts → Expiring window changes to match
14.7 | 14 | Change your password, log out, log in with the new one | Works; old one rejected
14.8 | 14 | Save a setting, then open the app on a **second device** | The change is there
14.9 | 14 | Enter a bad GSTIN / an obviously wrong PAN | Either validated, or at minimum it doesn't corrupt the invoice
15 · Backup, exports and reports
15.1 | 15 | Export Members / Payments / Expenses reports | Each downloads, opens in Excel, columns aligned
15.2 | 15 | Count rows in the Members export vs the member count on screen | Equal
15.3 | 15 | Sum the Payments export vs Finance → All Time revenue | Equal. If they differ, that is a finding, full stop
15.4 | 15 | Export with a name containing a comma, quote or `#` | Columns don't shift
15.5 | 15 | Full Data Backup | Downloads, non-empty, contains members + payments + expenses
15.6 | 15 | Financial & GST Audit Support Report | Totals match Finance. Identity fields populated. No "undefined"/"Not supplied" where you filled it in
15.7 | 15 | Do an export, then delete a member permanently, then export again | Difference is exactly that member
15.8 | 15 | Export when a date filter is applied | Export honours the filter — or clearly states it doesn't
15.9 | 15 | As staff 🔒 | Backup page unreachable
16 · Overview / dashboard / analytics
16.1 | 16 | Every number on Overview, cross-checked against its own page | Revenue = Finance. Members = Members list. Dues = Alerts. Expiring = Alerts
16.2 | 16 | Click every stat card and mini-stat | Navigates to the right page **with the right filter applied**
16.3 | 16 | Analytics page, every chart | Loads, no console errors, figures agree with Finance
16.4 | 16 | Analytics with a period changed | Charts update; totals still reconcile
16.5 | 16 | Recent activity list | Shows the things you actually just did, in the right order
16.6 | 16 | Overview with zero members (or filter to an empty period) | Empty states, not `NaN`, `undefined`, `₹NaN` or a broken chart
16.7 | 16 | As staff 🔒 Overview | No financial figures
17 · Cross-cutting — run these last, they find the ugly ones
17.1 | 17 | **The full lifecycle in one go:** enquiry → convert to member → partial payment → collect balance → renew → check in twice → generate invoice → remove permanently. After *every single step*, glance at Finance, Overview and Alerts | Every number moves by exactly the right amount, every time
17.2 | 17 | Browser **Back button** after every navigation: dashboard sections, modals, member portal tabs, desk display | Goes somewhere sensible. Never a blank screen, never logged out, never stuck
17.3 | 17 | Open two tabs, change something in tab A, refresh tab B | Tab B shows the change
17.4 | 17 | Leave the app open for 30+ minutes, then click something | Still works, or asks you to log in again cleanly. Not a silent failure or a stale-token error
17.5 | 17 | Every modal: open it, press Escape, click outside, press the X | All three close it. Nothing left stuck on screen behind it
17.6 | 17 | Every form: submit it **empty** | Clear validation messages, no crash
17.7 | 17 | Every list with a search box: search for text that matches nothing | Clean "no results", not a blank page
17.8 | 17 | Long member name (60+ characters) and a very long note | No layout break in the list, modal, invoice or export
17.9 | 17 | Phone (390px): every page, every table, every modal | Nothing cut off, nothing needing horizontal scroll, buttons reachable, the floating + button doesn't cover anything you need
17.10 | 17 | Anywhere a number is shown: check ₹ formatting | Indian format (₹1,25,000), consistent everywhere, no `1.25e5`, no missing symbol
17.11 | 17 | Check the same figure on desktop and phone | Identical
17.12 | 17 | Log out from the member portal, then press Back | Cannot get back into the portal without logging in
17.13 | 17 | While logged out, type a dashboard URL directly | Redirected to login, not a flash of real data first
18 · Cleanup — do not skip
18.1 | 18 | Delete every `ZZTEST-` member, enquiry, expense, plan and staff login you created
18.2 | 18 | Confirm Finance → All Time revenue is back to the number you recorded at the start of testing
18.3 | 18 | Confirm the member count is back to its starting value
18.4 | 18 | List anything you could not delete, so the developer can clean it up